## Global Dashboard
NBC 2021 WORKPLAN IMPLEMENTATION DASHBOARD (SUMMARY) |  |  | Date when last updated | 2020-01-18
# | DEPARTMENT | PROGRESS |  | Overall 2021 achievement
1.0 | NBC Ngong Road | #REF! |  | #REF!
2.0 | NBC Kibera | #REF!
3.0 | NBC Ongata Rongai | 29.44%
4.0 | NBC Westlands | #REF!
5.0 | NBC Kikuyu | #REF!
6.0 | NBC Kitengela | #REF!
7.0 | Global Missions & Outreach | 33.46% |  | KEY
8.0 | Administry | #REF! |  | Excellent
Good
Fair
Not so good
Worrying

## NBC ORongai
WORKPLAN & APPRAISAL TOOL FOR YEAR: 2021 Ongata Rongai
[14 empty] | Overall achievement | 29.44%
NAME OF ASSEMBLY/DEPT: |  |  |  | NAME: | Rev Abednego Kasimu |  | Qtr of year |  |  |  | Qtr of year |  |  |  |  | (only for Assembly/departmental workplan)
[7 empty] | Planned Implementation |  |  |  | Actual Implementation |  |  |  | Progress | BUDGET | SELF FUNDING | BUDGET Request | NARRATIVE REPORT |  |  |  | Appraisal
Goal by 2023 & Target | Outcome(s) | Outcome indicator(s) | BASELINE 2019 | TARGET 2023 | 2021 Activities | TARGET/ INDICATOR | I | II | III | IV | I | II | III | IV | (auto-calculated) |  |  |  | 1ST QUARTER | 2ND QUARTER | 3RD QUARTER | 4TH QUARTER | SELF | SUPERVISOR
There is increased spiritual engagement and expression of regular congregants through worship, prayer and the word; Level of congregants engagement measured as good (from 75% to 85%) | 1.1 Congregants expressing and experiencing Christ-centered, vibrant and relevant worship | Proportion of worship content that is Christ-centered | 87% | Keep it at at least 90% | Invite music teams who will lead Christ-centered music (Honorarium for visitng music teams and preachers including youth service) | 4 | [8 empty] | 0% | 100000 |  | 100000 | bar: Planned Implementation I to Planned Implementation IV
[5 empty] | Holy Communion every month | 12 | Planned Implementation I: 3; Planned Implementation II: 3; Planned Implementation III: 3; Planned Implementation IV: 3 | 0% | 20000 |  | 20000
[5 empty] | Training for worship team | 1 | [8 empty] | 0% |  |  | 0 | bar: Planned Implementation II
[5 empty] | Dedicate Monday's as prayer day for worship team (so as to hear from God) qtly report | 4 | [8 empty] | 0% |  |  | 0 | bar: Planned Implementation I to Planned Implementation IV
[5 empty] | Various expression of worship through creative arts at least once a quarter | 4 | [8 empty] | 0% |  |  | 0 | bar: Planned Implementation I to Planned Implementation IV
0
|  | Level of congregations responsiveness to the worship | 63% | Keep it at at least 80% | [13 empty] | 0
0
0
0
0
0
0
| 1.2 Congregants are increasingly engaged in fervent, continuous prayer empowered by the Holy Spirit | Proportion of people engaged in fervent, continuous prayer | 44% | Keep it at at least 70% | Recruit additional 7 new intercessors (from the current 8) | 7 | Planned Implementation I: 7; Actual Implementation I: 7 | 100% | 20000 |  | 20000 | We have successfully recruited more than 7 new intersessors cutting across all ministries i.e. (The Men, Women and Youth Ministries)
[5 empty] | Training for intercessers. | 2 | [8 empty] | 50% |  |  | 0 | We held an introductory training session via zoom. | bar: Planned Implementation I; Planned Implementation III; Actual Implementation I
[5 empty] | Women praying weekly in a two-day prayer chain | 48 | 12 | 12 | 12 | 12 | 12 | 12 |  |  | 50% |  |  | 0 | Women continue to pray every Wednesday for 24hrs
[5 empty] | Men meeting together every 2 weeks for prayer | 26 | 6 | 6 | 6 |  | 6 | 4 |  |  | 55.56% |  |  | 0 | Since physical meetings have been a bit of a challenge the men have been meeting regularly on zoom and have a consistent prayer chain every Wednesday.
[5 empty] | Youth leaders praying every Saturday morning | 48 | 12 | 12 | 12 | 12 | 12 | 12 |  |  | 50% |  |  |  | The Youth leadership has been having weekly prayers every Saturday morning via calls.
0
0
0
|  | # of prayer initiatives currently in place |  |  | Strengthen monthly 1st Sunday prayer meeting | 12 | 3 | 3 | 3 | 3 |  | 3 |  |  | 25% | 0 |  | 0
[5 empty] | Hold 48 weekly prayer meeting (Friday) | 48 | 12 | 12 | 12 | 12 | 12 | 12 |  |  | 50% |  |  | 0 | The Friday prayer service has been consistent since the year began every evening via our zoom platform.
[5 empty] | Hold 3 Keshas Facilitation & Hospitality (Honorarium for worship team) | 2 | Planned Implementation II: 1; Planned Implementation III: 1; Actual Implementation II: 0 | 0% | 40000 |  | 40000
[5 empty] | Congregational prayer and fasting in addition to global initiative | 3 | [8 empty] | 33.33% | bar: Planned Implementation II to Planned Implementation IV; Actual Implementation II
0
0
| 1.3 Congregants are experienceing and responding to Christ-centred and relevent preaching and teaching | Proportion of preaching and teaching that is Christ-like centred and relevant | 92% | Keep it at at least 90% | Invite preachers who will preach Christ-centered sermons (Honorarium for visitng music teams and preachers including youth service) | 4 | [8 empty] | 50% |  |  | 0 |  | No need for honorarium | bar: Planned Implementation I to Actual Implementation II
[5 empty] | Training of in-house preachers | 2 | Planned Implementation I: 1; Planned Implementation IV: 1; Actual Implementation II: 0 | 0% |  |  | 0
0
0
0
|  | Level of congregation's responsiveness to the preaching and teaching | 83% | Keep it at at least 80% | Conduct 2 Baptism Classes and Baptism in 2021 | 2 | Planned Implementation II: 1; Planned Implementation IV: 1; Actual Implementation II: 0 | 0% |  |  | 0
[5 empty] | Regular altar calls after preaching. Report on number of people who receive Christ in the services | 4 | [8 empty] | 25% |  |  | 0 |  | 5 people gave their lives | bar: Planned Implementation I to Planned Implementation IV; Actual Implementation II
[5 empty] | Report on testimonies from congregants out of the teachings | 4 | [8 empty] | 50% |  |  | 0 | Healing after prayers | Salvation of souls during funerals | bar: Planned Implementation I to Actual Implementation II
0
| 1.4 Congregants encountering quality ministry in every aspect of the worship service | Level of quality in every aspect of the worship service | 84% | Keep it at at least 90% | Equipping a team of at least 15 ushers and relevant training | 1 training | [8 empty] | 0% | 5000 |  | 5000 | bar: Planned Implementation II
[5 empty] | Recruit and equip a team of 15 welcomers (one from each growth group) | 1 training | [8 empty] | 0% | 5000 |  | 5000 | bar: Planned Implementation I
[5 empty] | Re-orientation for the 15 members of the hospitality team | 1 | [8 empty] | 0% | 5000 |  | 5000 | bar: Planned Implementation I
[5 empty] | Décor. Have a décor ministry team | 1 | [8 empty] | 100% | 80000 |  | 80000 | The complete décor team was recruited and are actively serving | bar: Planned Implementation I; Actual Implementation I
[5 empty] | Reconstitute Holy communion ministry team | 1 | [8 empty] | 100% |  |  | 0 | Additional members were recruited into the existing Holy Communion Team. Majority members of the older team were seniors who are currently not attending service. | bar: Planned Implementation I; Actual Implementation I
0
0
There is increased spiritual maturity of regular congregants through effective discipleship, mentorship and leadership development; At least 50% of regular congregants, at any given time, who understand, communicate and live out the gospel | 2.1 Congregants effectively discipled and discipling others | # of congregants being discipled | 50% | 60% | Have ROPES program targeting 25 kids through the year in 2021 (Qtly reports) | 4 | 1 | 1 | 1 | 1 | 1 | 0 |  |  | 25% | 110000 | 55000 | 55000 | Classes for the ROPErs began when Sunday school resumed at the beginning of the year and after that we could not continue online because many children couldn’t afford bundles | school calendar affected us
[5 empty] | Target at least 350 children in our Holiday Bible club by end 2021 | 3 | Planned Implementation II: 1; Planned Implementation III: 1; Planned Implementation IV: 1; Actual Implementation II: 0 | 0% | 200000 |  | 200000 |  | Covid situation
[5 empty] | Holiday High schoolers holiday sessions | 3 | Planned Implementation II: 1; Planned Implementation III: 1; Planned Implementation IV: 1; Actual Implementation II: 0 | 0% | 50000 |  | 50000
[5 empty] | 2021n Excan Program | 1 | [8 empty] | 100% | 35000 | 15000 | 20000 | bar: Planned Implementation II; Actual Implementation II
[5 empty] | Have at least 6 active youth Growth Groups by end of 2021 | 4 new group | Planned Implementation II: 2; Planned Implementation IV: 2; Actual Implementation I: 2; Actual Implementation II: 2 | 100% |  |  | 0 | We managed to start 2 new youth bible study groups.
[5 empty] | Bible study material facilitation - Youth ministry | 4 | [8 empty] | 50% | 16000 | 5000 | 11000 | We acquired a few online resources to help fascilitate our weekley bible study sessions. | bar: Planned Implementation I to Actual Implementation II
[5 empty] | Effective Couples Ministry in 2021 targetting 30 couples with 3 meetings | 3 | [8 empty] | 33.33% | 100000 | 70000 | 30000 | bar: Planned Implementation I to Planned Implementation III; Actual Implementation II
[5 empty] | Do 1 Parenting seminar in 2021 | 1 | Planned Implementation IV: 1; Actual Implementation II: 0 | 0% | 105000 | 50000 | 55000
[5 empty] | Do 2 Child dedication in 2021 | 2 | Planned Implementation II: 1; Planned Implementation IV: 1; Actual Implementation II: 0 | 0% | 0 |  | 0
[5 empty] | Do 1 Family day in 2021: | 1 | Planned Implementation IV: 1; Actual Implementation II: 0 | 0% | 150000 | 50000 | 100000
[5 empty] | Timely availabity of relevant Bible study Materials: Growth groups | 4 | [8 empty] | 50% | 100000 | 100000 | 0 | Materials were availled for the Growth group as required. | bar: Planned Implementation I to Actual Implementation II
0
|  | # of congregants discipling others | 46% | 55% | Have at least one session for disciplers | 1 | [8 empty] | 0% |  |  | 0 | bar: Planned Implementation I
[5 empty] | Recruit disciplers for ROPES and KUPAA participants | 1 | [8 empty] | 0% |  |  | 0 | bar: Planned Implementation I
[5 empty] | One joint sessions for those in discipleship relationships | 1 | [8 empty] | 0% |  |  | 0 | bar: Planned Implementation IV
0
0
| 2.2 Increased number of persons involved in mentorship programs | # ofpersons involved in mentorship programs - being mentored | 29% | 40% | Launch and establish KUPAA ministry in 2021 (honorarium for some of the speakers, snacks, transportation incase of site visits) | 1 | [8 empty] | 100% | 30000 |  | 30000 | Plans have been underway to mobilize the fascilitators and we are aiming to have the launch in May. | bar: Planned Implementation I; Actual Implementation II
0
0
0
0
0
|  | # of persons involved in mentorship others | 27% | 40% | [13 empty] | 0
0
0
0
0
0
0
| 2.3 Visible and active leadership development | # of Leadership development initiatives | 86 in diff ministries across assemblies | 100 initiatives | Recruit and have 3 trainings for 30 teachers | 3 | Planned Implementation I: 1; Planned Implementation II: 1; Planned Implementation III: 1; Actual Implementation II: 0 | 0% | 45000 |  | 45000 | Teachers had their first training in February
[5 empty] | Have 2 Co-workers fellowships targetting 100 leaders by end of 2021 | 2 | [8 empty] | 50% | 110000 |  | 110000 | bar: Planned Implementation I; Planned Implementation IV; Actual Implementation II
[5 empty] | Monthly Coworkers meetings | 10 | Planned Implementation I: 2; Planned Implementation II: 3; Planned Implementation III: 3; Planned Implementation IV: 2 | 0% | 0 |  | 0
[5 empty] | Do 3 Growth Group leaders meetings for training fellowship and support including youth Bible study | 3 | [8 empty] | 66.67% | 20000 |  | 20000 | Growth Group leaders met for their first meeting to begin the year together, debrieft and enrich one another on doing growth groups during the pandemic | bar: Planned Implementation I to Planned Implementation III; Actual Implementation I to Actual Implementation II
[5 empty] | Do Leadership meetings and 1 retreat/training | 4 | [8 empty] | 25% | 30000 |  | 30000 | bar: Planned Implementation I to Planned Implementation IV; Actual Implementation II
[5 empty] | Monthly ministry evaluation meetings for youth leaders | 12 | 3 | 3 | 3 | 3 | 3 | 3 |  |  | 50% | 12000 |  | 12000 | The Youth monthly ministry leadership review meetings have been held every second Saturday via zoom.
0
0
|  | # of participants in the Leadership development initatives | TBC |  | # of teachers trained in the 3 teacher trainings | 3 | 1 | 1 | 1 |  | 1 | 0 |  |  | 33.33% |  |  | 0 | The first Sunday school training and fellowship had 14 Teachers
[5 empty] | # of participants in the 2 Co-workers fellowships | 2 | Planned Implementation I: 1; Planned Implementation IV: 1; Actual Implementation II: 2 | 100% |  |  | 0
[5 empty] | average # of participants in Monthly Coworkers meetings | 10 | Planned Implementation I: 2; Planned Implementation II: 3; Planned Implementation III: 3; Planned Implementation IV: 2 | 0% |  |  | 0
[5 empty] | # of participants in the Growth Group leaders meetings/fellowships (including youth Bible study) | 3 | [8 empty] | 66.67% |  |  | 0 | The first meeting had 12 Growth group leaders, Most groups were represented | bar: Planned Implementation I to Planned Implementation III; Actual Implementation I to Actual Implementation II
[5 empty] | # of participants in the Leadership meetings and 1 retreat/training | 4 | [8 empty] | 25% |  |  | 0 | bar: Planned Implementation I to Planned Implementation IV; Actual Implementation II
[5 empty] | Average # of participants in the Monthly ministry evaluation meetings for youth leaders | 12 | 3 | 3 | 3 | 3 |  | 8 |  |  | 66.67% |  |  | 0
| 2.4 Visible and active fellowship oriented forums | Level of involvement/Participation in fellowship/care ministries | 12% | 40% | Teachers Quaterly Fellowship and support Meetings: | 4 | [8 empty] | 50% | 15000 |  | 15000 | Sunday School Teacher met as sundayschool resumed to agree on way forward. | bar: Planned Implementation I to Actual Implementation II
[5 empty] | Grow Men’s ministry in 2021 targeting 60 men per meeting | 4 | [8 empty] | 25% | 80000 | 50000 | 30000 | bar: Planned Implementation I to Planned Implementation IV; Actual Implementation II
[5 empty] | Strengthen Ladies Ministry in 2021 targeting 70 ladies in the monthly meeting | 10 | 2 | 3 | 3 | 2 | 2 | 2 |  |  | 40% | 100000 | 60000 | 40000 | Ladies had an in person meeting in February (Meet and Greet Prayer meeting) and a zoom meeting in March ( Mental Welness)
[5 empty] | DUNAMIS Conventions | 1 | [8 empty] | 0% | 200000 |  | 200000 | bar: Planned Implementation III
Regular congregants are participating in holistic outreach, evangelism and viable Church Planting; At least 60% of regular congregants participating; and 2 churches planted | 3.1 An equipped congregation that is actively and effectively engaged in holistic outreach. | Proportion of congregants who are enthusiastically and consistently involved in holistic outreach. | 22% | 55% | Medical Camp | [10 empty] | 0 |  | 0
[5 empty] | Support 3 Children in their Education | 3 | Planned Implementation I: 3; Actual Implementation I: 1; Actual Implementation II: 1 | 66.67% | 50000 |  | 50000
[5 empty] | Support of 5 children in highschool - transferred to GMO | [10 empty] | 250000 |  | 250000
[5 empty] | Support the walk in welfare needs of the sorrounding community | 4 | 1 | 1 | 1 | 1 | 1 | 0 |  |  | 25% | 50000 |  | 50000
0
0
| 3.2 An equipped congregation that is actively and effectively engaged in evangelism. | Proportion of congregants who are enthusiastically and consistently sharing the gospel of Christ. | 45% | 65% | Have 2 evangelism training in 2021 | 2 | [8 empty] | 0% | 20000 |  | 20000 | bar: Planned Implementation II; Planned Implementation IV
[5 empty] | Neighbourhood evangelism during mission month | 1 | [8 empty] | 0% | 20000 |  | 20000 | bar: Planned Implementation III
[5 empty] | Support and Participate in 1 Global mission in 2021 | [12 empty] | 0
0
0
0
0
| 3.3 Planted and established vibrant, Christ centered churces that are advancing the Kingdom of God. | # of congregations planted and established. | 3 | 5 | [13 empty] | 0
0
0
0
|  | # of strucutred ministries established in the church plants (Limited to the church plants including Children incl ROPES, youth, young adults and the fellowship/care ministries) | 28 | 35 | [13 empty] | 0
0
0
0
Children, Youth, and Young Adults are actively and variously engaged in influencing the world around them by living out and sharing their Christian testimony; At least 50% of Children, youth and young adults | 4.1 Children actively living out and sharing their Christian testimony | % of children living out and sharing their Christian testimony (home, school, play arenas etc) | 49% | 60% | Acquire curriculium for 270 kids in 2021 | 1 | [8 empty] | 0% | 15000 |  | 15000 | Additional matterials will be added once Sunday school resume and when need arise | bar: Planned Implementation I
[5 empty] | Acquire teaching aids for 7 Sunday School Classes | 1 | [8 empty] | 100% | 35000 |  | 35000 | Sunday school classes have mostly been on soom and we havent needed to procure any teaching aids | bar: Planned Implementation I; Actual Implementation I
[5 empty] | Do 4 Scripture championships | 4 | 1 | 1 | 1 | 1 | 1 | 0 |  |  | 25% | 5000 |  | 5000 | The children had an online Bible trivia
[5 empty] | Use of creative arts Quarterly | 4 | [8 empty] | 50% | 5000 |  | 5000 | Children were to worship through creativity in the adult church, We hope to do so once they resume. | bar: Planned Implementation I to Actual Implementation II
[5 empty] | Pastor/teacher to children visitation | 4 | 1 | 1 | 1 | 1 |  | 0 |  |  | 0% | 30000 |  | 30000 | This proved challenging during this pandemic season.
[5 empty] | Child reach child outreach | 1 | Planned Implementation II: 1; Actual Implementation I: 0; Actual Implementation II: 0 | 0% | 30000 |  | 30000
0
0
0
| 4.2 Youth actively living out and sharing their Christian testimony | % of youth (ages13-17) involved actively living out and sharing their Christian testimony (understand, communicate and living out the gospel) | 13% | 45% | Train and engage a team of at least 10 Youth for the JIWE teens service (Honorarium for trainer.) | 1 training | [8 empty] | 0% | 10000 |  | 10000 | bar: Planned Implementation II
[5 empty] | Strengthen a creative arts ministry in 2021 (refreshments and props) for teens ministry preparing skits for Easter and Christmas holidays | 4 | 1 | 1 | 1 | 1 | 0 |  |  |  | 0% | 10000 |  | 10000 | Due to covid restrictions and scarcity of resources (bundles and airtime for the team), we have had to put a pause on our relaunc of the Creative arts ministry.
0
| 4.3 Young adults actively living out and sharing their Christian testimony | % of young adults (ages 18-29) actively living out their Christian testimony (understand, communicate and living out the gospel) | 16% | 45% | Acquire necessary resources within the youth service to enable growth of up to 120 youth in 2021(Beautification of the youth sanctuary podium). | 1 | [8 empty] | 100% | 10000 |  | 10000 | We managed to put cabro and build a podium within the Youth sanctuary. | bar: Planned Implementation I; Actual Implementation I
[5 empty] | Have School of Word in 2021 | 1 | [8 empty] | 0% | 7000 |  | 7000 | bar: Planned Implementation II
[5 empty] | Rewards and appreciation culture once a month for bible trivia . | 10 | 2 | 3 | 3 | 2 | 2 | 2 |  |  | 40% | 12000 |  | 12000 | We managed to have bible trivia review questions for every last Sunday of February and March.
[5 empty] | Establish a pre-service youth prayer team (qtly reporting) | 4 | [8 empty] | 0% |  |  | 0 | bar: Planned Implementation I to Planned Implementation IV
[5 empty] | Sensitize and Train Youth in outreach and evangelism within their service and also in the church. | 1 | [8 empty] | 0% | 0 |  | 0 | bar: Planned Implementation III
[5 empty] | Have youth involved in 2 outreach activities in the year 2021 | 2 | Planned Implementation II: 1; Planned Implementation III: 1; Actual Implementation I: 0 | 0% | 50000 | 15000 | 35000
[5 empty] | One Youth Outreach Concert | 1 | Planned Implementation II: 1; Actual Implementation I: 0 | 0% | 50000 |  | 50000
[5 empty] | 1 Youth sports outreach initiatives | 1 | Planned Implementation IV: 1; Actual Implementation I: 0 | 0% | 60000 |  | 60000
[5 empty] | 10 Youth Hangout sessions | 10 | 2 | 3 | 3 | 2 | 2 | 3 |  |  | 50% | 50000 |  | 50000 | We managed to have 3 hangouts this year.
[5 empty] | 1 Youth Camp | 1 | Planned Implementation IV: 1; Actual Implementation I: 0 | 0% | 200000 | 100000 | 100000
Governance and management structures are aligned and strengthened effectively overseeing the affairs of NBC and its growth; Alignment and strength of governance and management structures rated as good | 5.1 Governance and management structures are fully aligned to the changing structure of the church | % level of alignment across the entire NBC | 72% | 95% | [13 empty] | 0
0
0
0
| 5.2 Governance and management structures strengthened to effecitvely give oversight to the growing and dynamic church | Level of strengthening attained | 70% | 95% | Have 1 open day meeting | 1 | Planned Implementation IV: 1; Actual Implementation I: 0 | 0% |  |  | 0
0
0
0
| 5.3 Increased Registered Membership | % increased propotion of members | 31% | At least 50% of congregation at any one time are members | Do 2 Membership Classes in 2021 | 2 | [8 empty] | 50% | 30000 |  | 30000 | bar: Planned Implementation II; Planned Implementation IV to Actual Implementation I
0
0
0
| Lead Pastor's Key Ministry Areas Summary | 6.1 Community presented with the Gospel of Christ | Ministry activities that result to salvation to those who do not know God |  | Report on Number of people who have given their lives to Christ as Lord and Saviour in Church and through outreach initiatives | 4 | [8 empty] | 25% |  |  | 0 | bar: Planned Implementation I to Actual Implementation I
Lead Pastor's Key Ministry Areas Summary |  | 6.2 Resource Mobilization done so as to sustain ministry activities | Ministries of the church have been sufficiently supported |  | Report on Church giving for the year; target is to achieve at least 80% (Target: Offering-Kshs8.5m and Fundraising (LTAxe)-Kshs 1.280m) | 4 | [8 empty] | 50% |  |  | 0 | bar: Planned Implementation I to Actual Implementation II
|  | 6.3 Member Care: Visitation and Benevolence | Congregation is cared for and nurtured |  | Report on number of visitation, counselling and benevolence contacts per quarter. At least two Pastoral visits to congregant family per month | 4 | [8 empty] | 50% |  |  | 0 | bar: Planned Implementation I to Actual Implementation II
|  | 6.4 Preaching Ministry | Involvement in the Preaching Ministry of the assembly and NBC in general |  | Report on number of preaching assignments carried out per quarter | 48 | 12 | 12 | 12 | 12 | 12 |  |  |  | 25% |  |  | 0
|  | 6.5 Capacity building for Assembly staff team |  |  | Report on activities undertaken to build/strengthen staff team and build capacity or competencies | 3 | [8 empty] | 0% | bar: Planned Implementation II to Planned Implementation IV
|  | 6.6 Involvement with other NBC Global matters | Engagement with the Church as assigned to various Committees by Senior Pastor |  | Quarterly report on involvement in meeting(s) or forums excluding SMT meetings | 4 | [8 empty] | 50% |  |  | 0 | bar: Planned Implementation I to Actual Implementation II
CRITICAL SUPPORT/ADMINISTRATIVE ITEMS | Administrative support | Effective Sunday Service support |  |  | 8. Sound & Music Equipment Maintainace | [10 empty] | 30000 |  | 30000
[5 empty] | 9. Purchase of Batteries for the cordless microphone | [10 empty] | 50000 |  | 50000
[5 empty] | 10. Media Support | [10 empty] | 80000 |  | 80000
[5 empty] | 11. Facilitation and equiping of the Worship team | [10 empty] | 80000 |  | 80000
[5 empty] | 12. Effective facilitation of Sunday Armed Security | [10 empty] | 104000 |  | 104000
[5 empty] | 13. Effective facilitation of Sunday Casuals including 2 Tea Ladies (@550/=),2 Sunday casuals(@550/=) | [10 empty] | 114400 |  | 114400
[5 empty] | 14. Effective facilitation of Sunday Boonhouse bus | [10 empty] | 300000 |  | 300000
[5 empty] | 15. Sunday Bulletin & Publication | [10 empty] | 80000 |  | 80000
[5 empty] | 18. Hire of 1 sound technician (@ 8,000/= Monthly) | [10 empty] | 96000 |  | 96000
[5 empty] | 19. Sunday Hospitality (Tea items and snacks) catering for 550pax including children | [10 empty] | 250000 |  | 250000
[5 empty] | 20. Sunday Cutllery & Utensils | [10 empty] | 40000 |  | 40000
[5 empty] | 21. Sunday Toiletries:-Toilet balls and Toilet paper | [10 empty] | 16000 |  | 16000
[5 empty] | 22. Sunday Drinking water | [10 empty] | 40000 |  | 40000
[5 empty] | 2. Maintenance of the kids play area & Sunday school classes furniture | [12 empty] | 0
[5 empty] | FIRST AID KITT REFILL | [10 empty] | 10000 |  | 10000
|  | Pastoral Care |  |  | 12. Pastors discretion: | [10 empty] | 50000 |  | 50000
[5 empty] | 13. Pastoral Care and Benevolence | [10 empty] | 200000 |  | 200000
|  | Utilities |  |  | 1. WATER BILLS | [10 empty] | 96000 |  | 96000
[5 empty] | 2. ELECTRICITY BILLS | [10 empty] | 96000 |  | 96000
[5 empty] | 3. TELEPHONE BILLS | [10 empty] | 72000 |  | 72000
[5 empty] | 4. INTERNET COSTS | [10 empty] | 66000 |  | 66000
|  | Office Operations |  |  | OFFICE TRANSPORT | [10 empty] | 50000 |  | 50000
[5 empty] | CLEANING COSTS | [10 empty] | 240000 |  | 240000
[5 empty] | SECURITY COSTS | [10 empty] | 885000 |  | 885000
[5 empty] | BANK CHARGES | [10 empty] | 60000 |  | 60000
[5 empty] | PROPERTY INSURANCE | [10 empty] | 30000 |  | 30000
[5 empty] | STATIONERY | [10 empty] | 30000 |  | 30000
[5 empty] | TONERS & STAMP INK | [10 empty] | 30000 |  | 30000
[5 empty] | TENT & EQUIPMENT LEASE | [10 empty] | 780000 |  | 780000
[5 empty] | SIGNAGE DESIGN & FABRICATION & COUNCIL FEES (3) | [10 empty] | 120000 |  | 120000
[5 empty] | MAINTENANCE | [10 empty] | 297500 |  | 297500
|  | Staff Welfare |  |  | 1. 10am & 4pm TEA Facilitation | [10 empty] | 250000 |  | 250000
[5 empty] | 2. lunch for staff working out of office | [12 empty] | 0
[5 empty] | OFFICE NEWSPAPER | [10 empty] | 20000 |  | 20000
|  | Caretakers housing |  |  | 1. HOUSE RENT | [10 empty] | 180000 |  | 180000
[5 empty] | 2. WATER BILLS | [10 empty] | 12000 |  | 12000
[5 empty] | 3. GARBAGE COLLECTION | [10 empty] | 4800 |  | 4800
[5 empty] | 4. SECURITY | [10 empty] | 4800 |  | 4800
|  | Personnel Costs |  |  | STAFF COSTS | [10 empty] | 8393685.8452 |  | 8393685.8452
|  | Capex; Equipment purchase |  |  | 5. Buy 3 TV screens in 2021 | [12 empty] | 0
[5 empty] | 6. Buy 100 additional chairs for pre-schoolers and Junior schoolers | [12 empty] | 0
[5 empty] | 7. Buying Audio visual equipment that will facilitate our children sanctuary worship | [12 empty] | 0
[5 empty] | TOTAL BUDGET | [10 empty] | 16040185.8452 | 570000 | 15470185.8452
[16 empty] | Approved budget: |  | 15470185.8452
| Signed by employee: |  |  | Date:
| Signed by Supervisor: |  |  | Date:

## GMO
WORKPLAN & APPRAISAL TOOL FOR YEAR: 2020
[14 empty] | Overall achievement | 33.46%
| NAME OF ASSEMBLY/DEPT: |  |  | NAME: | GMO |  | Qtr of year |  |  |  | Qtr of year |  |  |  |  | (only for Assembly/departmental workplan)
[7 empty] | Planned Implementation |  |  |  | Actual Implementation |  |  |  | Progress | BUDGET | SELF FUNDING | BUDGET Request | NARRATIVE REPORT |  |  |  | Appraisal
Goal by 2023 & Target | Outcome(s) | Outcome indicator(s) | BASELINE 2019 | TARGET 2023 | 2021 Activities | TARGET/ INDICATOR | I | II | III | IV | I | II | III | IV | (auto-calculated) |  |  |  | 1ST QUARTER | 2ND QUARTER | 3RD QUARTER | 4TH QUARTER | SELF | SUPERVISOR
There is increased spiritual engagement and expression of regular congregants through worship, prayer and the word; Level of congregants engagement measured as good (from 75% to 85%) | 1.1 Congregants expressing and experiencing Christ-centered, vibrant and relevant worship | Proportion of worship content that is Christ-centered | 87% | Keep it at at least 90%
|  | Level of congregations responsiveness to the worship | 63% | Keep it at at least 80%
| 1.2 Congregants are increasingly engaged in fervent, continuous prayer empowered by the Holy Spirit | Proportion of people engaged in fervent, continuous prayer | 44% | Keep it at at least 70%
# of prayer initiatives currently in place
| 1.3 Congregants are experienceing and responding to Christ-centred and relevent preaching and teaching | Proportion of preaching and teaching that is Christ-like centred and relevant | 92% | Keep it at at least 90%
|  | Level of congregation's responsiveness to the preaching and teaching | 83% | Keep it at at least 80%
| 1.4 Congregants encountering quality ministry in every aspect of the worship service | Level of quality in every aspect of the worship service | 84% | Keep it at at least 90%
There is increased spiritual maturity of regular congregants through effective discipleship, mentorship and leadership development; At least 50% of regular congregants, at any given time, who understand, communicate and live out the gospel | 2.1 Congregants effectively discipled and discipling others | # of congregants being discipled | 50% | 60%
|  | # of congregants discipling others | 46% | 55%
| 2.2 Increased number of persons involved in mentorship programs | # ofpersons involved in mentorship programs - being mentored | 29% | 40%
|  | # of persons involved in mentorship others | 27% | 40%
| 2.3 Visible and active leadership development | # of Leadership development initiatives | 86 in diff ministries across assemblies | 100 initiatives
|  | # of participants in the Leadership development initatives | TBC
| 2.4 Visible and active fellowship oriented forums | Level of involvement/Participation in fellowship/care ministries | 12% | 40%
Regular congregants are participating in holistic outreach, evangelism and viable Church Planting; At least 60% of regular congregants participating; and 2 churches planted | 3.1 An equipped congregation that is actively and effectively engaged in holistic outreach. | Proportion of congregants who are enthusiastically and consistently involved in holistic outreach. | 22% | 55% | KIBRA: Outreach through Medi-care, report on patients seen & congregants involved Report on one medical camp. Qtly report | 4 | [8 empty] | 50% | 100000 | 0 | 100000 | Being early in the year and the the current Covid situation, we did not have any plans for medical outreach. For the three months we have seen 1164 clients with varied illnesses. We thank God that we have not encountered any Covid related case. | The second quarter has been smooth in terms of operations. We have seen 876 clients with varied illnesses. The nurse has been successfully attending workshops organized by the subcounty aimed at improving health care offered in the community. | bar: Planned Implementation I to Actual Implementation II
[5 empty] | KIBRA: Outreach through Medi-care, therapy and social-economic support to HIV infected patients, number of sessions | 48 | 12 | 12 | 12 | 12 | 12 | 12 |  |  | 50% | 254000 | 0 | 254000 | The support group has had 12 successful sessions. There are 28 members, 5 new clients joined this year. For most, their source of livelihood have beed adversely affected with the pandemic. We have a few who have been in and out of hospital. | Chemichemi support group received 2 more members mid year. The team is doing well healthwise, save for isolated cases of normal illnesses. There has been a greater challenge of feeding their families. We were able to do one distribution of lovebox, but the need is greater.
[5 empty] | KIBRA: Submission of reports to the county in compliance to MoH set standards | 100 | 100 | 100 | 100 | 100 | 100 | 100 |  |  | 50% | 0 | 0 | 0 | Reports have been successfully submited to the county. We have been ranked favorably among the preferable facilities in the community by the subcounty | Reports have been successfully sub,itted to the subcounty health board. We continue in keeping with the issued directives. The clinic received a new improved KEPI fridge from Save the Children international
[5 empty] | KIBRA: Ensure availability of drugs and reagents and that the pharmacy is well maintained (ensure reconciled system and actual stock of medicines) | 100 | 100 | 100 | 100 | 100 | 100 | 100 |  |  | 50% | 1200000 | 1200000 | 0 | Drugs and lab reagents have been promptly ordered and supplied. Banda Health System is operational. | We have had good and timely supply of drugs supply of drugs
[5 empty] | KIBRA: Weekly special clinics; report on numbers in CWC and ANC visits | 1 | Planned Implementation II: 1; Actual Implementation I: 0; Actual Implementation II: 1 | 100% | 30000 | 0 | 30000 | The ANC and CWC clinics have registered improved numbers. We have introduced sms based reminding system that has worked well to ensure children do not miss their immunizations. ANC clients are at an average of 14 per month. The children are at 146 monthly average | In the quarter we have seen 394 CWC clients, this is due to the targeted advertising that the volunteers have been doing in the Makina area. For ANC mothers, we have 9 new clients and 29 revisits.
[5 empty] | KIBRA: Promotion of Reproductive Health Initiatives | 4 | 1 | 1 | 1 | 1 | 0 | 1 |  |  | 25% | 30000 | 0 | 30000 | We have not been able to do any health outreach due to the current health risk | In conjunction with Beyond Zero Karanja clinic, we successfully conducted HPV vaccinations outreach targeting school going girls. 60 girls from two schools were reached.
[5 empty] | SW: Outreach through high school education | 50 beneficiaries | Planned Implementation I: 50; Actual Implementation I: 56; Actual Implementation II: 52 | 216% | 2500000 |  | 2500000 | Resumption of High schools resulted in requisitions. 6 Students supported previously in NBC Rongai were absorbed by GMO under an SMT MInute | High school education ongoing
[5 empty] | SW: Outreach through college/University Education | 20 Beficiaries | Planned Implementation I: 20; Actual Implementation I: 13; Actual Implementation II: 20 | 165% | 1000000 |  | 1000000 | First year students reporting back to respective colleges for admission | Students admitted to college. Internship placement of Rita Nancy also done in this period.
[5 empty] | SW: Extended time of discipleship of Bapo Scholars through students camp | 1 Camp | Planned Implementation IV: 1; Actual Implementation I: 0; Actual Implementation II: 0 | 0% | 200000 |  | 200000
[5 empty] | SW: Social welfare to others: fees balances and sponsor to other students. | 6 Cases | Planned Implementation I: 2; Planned Implementation II: 2; Planned Implementation III: 2; Actual Implementation I: 0 | 0% | 60000 |  | 60000 | 2 requests received. Had meeting with the 1 client but not convinced of their desire to complete school as no effort from them yet. additional information needed verification ongoing.
[5 empty] | SW: Mentorship/Tution forums for sponsored students | 5 |  | 2 | 2 | 1 | 0 | 2 | 1 |  | 60% | 60000 |  | 60000 | Mentors following up with the students online due to Covid restrictions | College selection and placement training with the Ex Candidates most placed in a college. Pending is a south sudanese refugee student as they cannont access governemnt sponsored program.
[5 empty] | SW: Emergency fund | 3 Responses | 1 | 1 | 1 |  | 1 | 0 |  |  | 33.33% | 90000 |  | 90000 | Internship college placement for Rita Nancy in Vihiga and Kajiado | Emergency medical treatment for Jaffar Nyawa a bapo scholar whose eyesight was failing. Facilitated three medical review visits to lions Eye hospital and purchase of glasses at Optica.
[5 empty] | SW: Food and toiletries for selected institutions that request support | 2 Institutions | Planned Implementation II: 1; Planned Implementation IV: 1; Actual Implementation I: 0; Actual Implementation II: 0 | 0% | 60000 |  | 60000
[5 empty] | SW: Other forms of support to non church members | Reporting on natutre & No | [8 empty] | 50% | 100000 |  | 100000 | bar: Planned Implementation I to Actual Implementation II
[5 empty] | SW: Food for immediate support for weekly clients | Reporting on natutre & No | [8 empty] | 50% | 161000 |  | 161000 | Ongoing food support to needy | bar: Planned Implementation I to Actual Implementation II
[5 empty] | SW: Love INC Ngong Road involvement | Report ad impact | 1 | 1 | 1 | 1 | 0 | 0 |  |  | 0% | 60000 |  | 60000
[5 empty] | SW: Repair & distribution of Wheelchairs | 25 chairs | 5 | 5 | 5 | 5 | 4 | 0 |  |  | 20% | 200000 | 50000 | 150000 | 3 Urgent wheel chair requests prioritized due to the covid protocols and 1 wheelchair repair done | 3 urgent wheelchair requests prioritized.1 walking frame and 1 crutch distibuted.
[5 empty] | SW: Disability conference and support meetings | 1 confrence | Planned Implementation III: 1; Actual Implementation I: 0; Actual Implementation II: 0 | 0% | 180500 | 30000 | 150500 |  | Persons with disability been more vulnerable to covid exposure especially in physical meetingsCovid restictions have made it difficult to hold the conference
[5 empty] | SW: Deaf ministry: interpretation & Training | 4 | [8 empty] | 50% | 330000 | 0 | 330000 | Sign language interpretation to The NBC Church service on going. Sign language interpretationTraining not yet | Sign language interpretation to The NBC Church service on going. Sign language interpretation training not yet done | bar: Planned Implementation I to Actual Implementation II
[5 empty] | SW: Disaster response ministry: report on involvement and # of people impacted | 50 | 12 | 13 | 13 | 12 | 0 | 0 |  |  | 0% | 100000 | 50000 | 50000
[5 empty] | SW: Disaster response ministry: report on involvement and # of people impacted | 1 | Planned Implementation IV: 1; Actual Implementation I: 0; Actual Implementation II: 0 | 0% |  |  | 0
[5 empty] | SW: Number of participants in Entrepreneurship support eg mentored | 40 | 10 | 10 | 10 | 10 |  | 28 |  |  | 70% | 513600 | 233600 | 280000 | Training of trainers done to 10 EMT members to equip them on mentoring. They will be the Mentors to Mentees. 28 Mentees identified and verification done. Placement of metees with Mentors ongoing | mentors following up with the mentees. Further selcetion of the mentees ongoing to remain with the serious ones. 2nd cohort Training of trainers for the mentors done to a new team of 10 mentors
[5 empty] | SW: Number of participants in Entrepreneurship support, mentoring & networking | 100 | Planned Implementation II: 50; Planned Implementation IV: 50; Actual Implementation I: 5; Actual Implementation II: 28 | 33% |  |  | 0 |  | mentors following up with the mentees. Further selcetion of the mentees ongoing to remain with the serious ones. 2nd cohort Training of trainers for the mentors done to a new team of 10 mentors
[5 empty] | KWALE: Outreach through provision of affordable, accessible , available health care to the community. Volunteers welcomed from the congregation. Qtly report on patients attended to | 4 | 1 | 1 | 1 | 1 | 0 | 1 |  |  | 25% | 20000 |  | 20000 | Late last year and early this year, number of patients was overwhelming due to the health personnel strike. Number of patients attended to was 2475. Covid 19 protocals was put into practise.
[5 empty] | KWALE: Outreach through partnership with other organisations like PS Kenya. | 12 | 3 | 3 | 3 | 3 | 1 | 3 |  |  | 33.33% |  |  | 0 | Outreaches are onhold at the moment due to Covid 19 challenges. Hoping to resume in second quarter.
[5 empty] | KWALE: Monthly submission of reports to the subcounty health department in compliance to MOH standards. | 100 | 100 | 100 | 100 | 100 | 100 | 100 |  |  | 50% |  |  | 0 | The clinic has always been submitting timely reports to Kwale. Before 5th of every month.
[5 empty] | KWALE: Quarterly stocking of drugs in the pharmacy. Use of bin cards and cloud based(Banda health) systems to avoid stockouts. | 100 | 100 | 100 | 100 | 100 | 100 | 100 |  |  | 50% | 1440000 | 540000 | 900000 | MEDs delivered drugs in the month of January 2021. MOH has also been supplying us with programme based drugs. Cloud based, Banda health programme is up and running.
[5 empty] | Kwale Youh discipleship meetings at DIMA | 36 | 0 | 12 | 12 | 12 | 0 | 12 |  |  | 33.33% |  |  |  |  | A weekly youth Discipleship takes place at Mbegani. About 25 young people gather to dance and learn from God's word.
[5 empty] | Kwale Home visis by Missionary for relationships | 110 | 2 | 36 | 36 | 36 | 0 | 24 |  |  | 21.82% |  |  |  |  | About 30 families have been visited. 2 got born again and are being discipled bimonthly. So far we have distributed food stuffs worth Kshs. 21000.
[5 empty] | KWALE: Home visits | 16 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | 50% | 5000 |  | 5000 | Two main home visits done this quarter. Mzee Hassan and Mbodze. Both patients are picking up well. | Refer to the above.
[5 empty] | KWALE: Child welfare clinic every Wednesday and ANC on daily basis. | 50 | 12 | 13 | 13 | 12 | 13 | 12 |  |  | 50% |  |  | 0 | No of children seen at the childrens' clinic-679. Family planning patients- 141.
[5 empty] | KWALE: Conduct at least one medical camp each year. |  | Planned Implementation II: 1; Actual Implementation I: 0; Actual Implementation II: 0 | 0% | 300000 | 150000 | 150000
[5 empty] | KWALE:Mazumalume pastors' taining programme. | 2 | [8 empty] | 50% | 50000 |  | 50000 | The training did not take place, the trainer was not available. The pastors met to fellowship. | The training did not take place, the books have not been delivered yet. The pastors met to fellowship. | bar: Planned Implementation I; Planned Implementation III; Actual Implementation I
[5 empty] | KWALE: Men's fellowship: Hydrocele camps | 2 | Planned Implementation I: 1; Planned Implementation III: 1; Actual Implementation I: 0 | 0% | 250000 | 154000 | 96000 | Did not take place due to the Covid pandemic. | Did not take place due to the Covid pandemic.
[5 empty] | KWALE: Outreach to youth and children | 2 | Planned Implementation II: 1; Planned Implementation III: 1; Actual Implementation I: 0 | 0% | 0 |  | 0 |  | 25 youths were trained on youth leadership. A seminar of all youths whereby 319 youths were taught on Christian identity.A weekly bible study of about 3o youths meets. These young people also learn dancing.
[5 empty] | KWALE: School ministry through PPI teaching of CRE | 40 |  | 10 | 20 | 10 | 5 | 10 |  |  | 37.5% | 50000 |  | 50000 |  | 6 members of the community were recruited and trained to teach PPI at Dima Primary School.
[5 empty] | KWALE: Development of playground | 1 | [8 empty] | 0% | 0 |  | 0 |  | Most likely due to Covid-19 the project has stalled | bar: Planned Implementation IV
[5 empty] | KWALE: Mission support | 5 | 1 | 2 | 1 | 1 | 1 |  |  |  | 20% | 150000 | 50962 | 99038 | Pastor Kingsley is on the ground now, mission support slowl actualising.
| 3.2 An equipped congregation that is actively and effectively engaged in evangelism. | Proportion of congregants who are enthusiastically and consistently sharing the gospel of Christ. | 45% | 65% | MM: Ensure continous trainign of thelogians who can articulate NBC theological and pulpit stand in and outside NBC. Qtly report | 4 | [8 empty] | 50% | 400000 |  | 400000 | Grace Wanjiku finished her course, Collins Osire on his last semister, Nuur extended his course, Hope on going | bar: Planned Implementation I to Actual Implementation II
[5 empty] | MM. Suppo to Pastor Cecilia for Theological studies | 1 | Planned Implementation II: 1; Actual Implementation I: 0; Actual Implementation II: 1 | 100% |  |  |  |  | One time support was done in June
[5 empty] | MM: Interns & trainess support. Qtly report | 4 | 1 | 1 | 1 | 1 | 0 |  |  |  | 0% | 1885097 |  | 1885097 | No interns were taken this year | No interns were taken this year
[5 empty] | MM: Support missionaries involved in sharing the gospel | 9 | 9 | 9 | 9 | 9 | 9 | 9 |  |  | 50% | 576000 |  | 576000 | Jimmy Wambua, Joseph Halake, Prestone Guyo, Mutua Hahiaini, John Mathya, Emily Stravens, Ruth Kioko, Paul Njagi | Jimmy Wambua, Joseph Halake, Prestone Guyo, Mutua Hahiaini, John Mathya, Emily Stravens, Ruth Kioko, Paul Njagi
[5 empty] | MM: Support mission agencies involved in outreach/missions | 10 | 10 | 10 | 10 | 10 | 10 | 10 |  |  | 50% | 750000 |  | 750000 | BTL, Daystar, Focus, Caring Friends, KCSF, Theovision, Youth for Christ, Tumaini kwa Watoto, CFC, Scripture Union | BTL, Daystar, Focus, Caring Friends, KCSF, Theovision, Youth for Christ, Tumaini kwa Watoto, CFC, Scripture Union
[5 empty] | MM: Monitoring and evaluation of missionaries and mission agencies | 12 | 3 | 3 | 3 | 3 | 0 | 0 |  |  | 0% | 60000 |  | 60000
[5 empty] | MM: Annual missionaries Family seminar | 1 | Planned Implementation IV: 1; Actual Implementation I: 0; Actual Implementation II: 0 | 0% | 75000 |  | 75000
[5 empty] | MM: Encourage and suppport short term missions. Half year reports | 2 | Planned Implementation II: 1; Planned Implementation IV: 1; Actual Implementation I: 0; Actual Implementation II: 0 | 0% | 120000 |  | 120000
[5 empty] | MM: Constant communication with Joni and Friends, EMBC, Park and Jengana. Qtly reports | 4 | 1 | 1 | 1 | 1 | 1 | 0 |  |  | 25% | 179093 |  | 179093
[5 empty] | MM: Support Nuur to work in Kwale. Qtly report and summary of his work | 4 | [8 empty] | 50% | 300000 |  | 300000 | Nuur & Hope being supported for upkeep | Nuur & Hope being supported for upkeep | bar: Planned Implementation I to Actual Implementation II
[5 empty] | NGRD: 1st Friday Outreach leaders and partners meeting (This will have training, think tanks and prayers) | 11 | 2 | 3 | 3 | 3 | 1 | 3 |  |  | 36.36% | 11000 |  | 11000 | The first engagement with the outreach leaders in the different campuses and the different ministries has been deeply encouraging. The leaders shared so many stories of how they have been able to reach out despite the COVID pandemic restrictions. The online space has been of great use where APPs like whatsapp.FACEBOOK, INSTAGRAM have been used by individuals to reach out. The leaders also then informed us on the trainings that they would like to have, the most obvious one is the use of the online space to reach out and the next one was one of following up and discipling young believers. We were to have another First friday in March but I got infected with COVID and was unable to carry it out. However, it has prompted the need to a leadership team who will champion these meetings, trainings and mission mobilization.
[5 empty] | NGRD: Campus engagement ( Reaching out to at least three campuses. | 3 | [8 empty] | 66.67% | 40000 |  | 40000 | Another deeply encouraging ministry has been that of the campus ministry. COVID in in it's restrictions provided an opportunity for NBC to engage with the MEDICAL school campus at a deepler level. We began conversations with them on hosting their meetings for campus in Baptist in the month of February, this began and we had in our first meeting over 70 students in attendance. The leaders invited us to even join in talks that thety were having with their different fellowships on zoom. The lock down has happened yet again and we have had to halt any meetings on site that doesn't have the restricted 15 members. However, there were different ministry engagement that developed because of this interaction and that is namely the worship ministry training of the MSCU worship teams and the sound and media team reaching out and mentoring students on and through sound. | bar: Planned Implementation I to Planned Implementation III; Actual Implementation I to Actual Implementation II
[5 empty] | NGRD: 4 Webniar Trainings in the year | 1 | 1 | 1 | 1 | 1 | 0 | 0 |  |  | 0% | 4000 |  | 4000 | The webniars as have been informed by the leaders will begin this month with the first training on following up on those that we have reached out to.
[5 empty] | NGRD: Report on and support participants engaged in outreach activities: 2 neighbourhood street evangelism, 1 far off mission, 1 institutional investigative Bible Study, 1 social welfare activity | 4 | 1 | 1 | 1 | 1 | 1 | 0 |  |  | 25% | 80000 |  | 80000 | Though this season has been hectic and almost stifling for any form of outreach. I am happy to report though that despite those prohibitions, the Lord's work went on and is still going on. 1 member reported that she was engaging people through Facebook and had almost 9,000 followers, another shared that she has been doing Bible study with some ladies from her neighbourhood and some even gave their lives to christ. The sunday school team has been joining the schools on their zoom assembly and even visiting some of the schools for PPI. Others in the church plant have deeply engaged in care and the families that have not had food they have rallied around and shared the love of Christ through the giving of food. Other ministries in NBC ngong road have found that they have increased in their outreach now that they have been using the online platform to reach out.
[5 empty] | NGRD: Having at least 10 staff members engaged in the planned outreach activities or adopt a community that they can reach out to | 10 | 4 | 3 | 3 |  | 4 | 2 |  |  | 60% | 0 |  | 0 | It has also been wonderful to see the staff team members actually joining in outreach activities like the First Friday outreach leaders meeting but to also share their own stories of outreach in their private circles. 6 members of staff have so far joined us which is amazing and even encouraging for themselves and the outreach leaders.
[5 empty] | NGRD: Have atleast 3 Evangelistic Sunday services.( This will happen every quarter and people will choose at the beginning of every quarter who they are praying for and desire to bring to the service) | 3 | [8 empty] | 0% | 0 |  | 0 | bar: Planned Implementation II to Planned Implementation IV
[5 empty] | NGRD: Marsabit follow up and discipleship support | 2 | [8 empty] | 50% | 125000 | 51000 | 74000 | We have been in touch with some members of the churches in Marsabit but due to the current lock down, it will be hard for us to travel for a follow up visit in this quarter | bar: Planned Implementation I; Planned Implementation III; Actual Implementation II
[5 empty] | NGRD: Have 1 far off mission ( a medical camp in Marsabit) | 1 | Planned Implementation IV: 1; Actual Implementation II: 0 | 0% | 200000 | 100000 | 100000
[5 empty] | FOS: Organize interfaith forums in Somali dominated areas | 2 | Planned Implementation II: 1; Planned Implementation IV: 1; Actual Implementation II: 0 | 0% | 20000 |  | 20000
[5 empty] | FOS: Show care to the vulnerable in the Somali community | 2 | Planned Implementation I: 1; Planned Implementation III: 1; Actual Implementation I: 0 | 0% | 15000 |  | 15000 | Has not been possible because of Covid-19 restrictions
[5 empty] | FOS: Training on apologetics, Somali language, digital ministry for outreach | 3 | Planned Implementation I: 1; Planned Implementation II: 1; Planned Implementation III: 1; Actual Implementation I: 0 | 0% | 20000 |  | 20000 | Planning for the 3rd quarter
[5 empty] | FOS: Prayers once a week | 44 | 10 | 12 | 12 | 10 | 10 | 10 |  |  | 45.45% | 10000 |  | 10000 | Prayers have been continuing every Tuesday at EFC at 1-2pm
[5 empty] | FOS: Prayer walks in Somali dominated areas | 4 | [8 empty] | 25% | 15000 |  | 15000 | I was part of 3 believers not from FOS team who were prayer walking on Fridays in Eastleigh | bar: Planned Implementation I to Actual Implementation I
[5 empty] | FOS: English and Kiswahili language ministry, at least 2 students a week | 43 | 11 | 12 | 12 | 8 | 11 |  |  |  | 25.58% | 9000 |  | 9000 | Interacted and taught basic English skills to 5 ladies and 1 young man
[5 empty] | FOS: School ministry through PPI (primary) and CU (secondary and higher institutions) | 25 | 10 | 10 | 5 |  | 7 | 7 |  |  | 56% | 10000 |  | 10000 | Taught PPI at Racecourse and shared in C.U. at Maina Wanjigi on Fridays
[5 empty] | FOS: Recreation activities such as sports, outings | 2 | [8 empty] | 0% | 20000 |  | 20000 | bar: Planned Implementation II to Planned Implementation III
[5 empty] | FOS: MBBs care to meet their felt needs as they arise | 1 | [8 empty] | 0% | 60000 |  | 60000 | bar: Planned Implementation II
[5 empty] | FOS: Specialized medical outreach | 1 | [8 empty] | 0% | 120000 |  | 120000 | bar: Planned Implementation II
| 3.3 Planted and established vibrant, Christ centered churces that are advancing the Kingdom of God. | # of congregations planted and established. | 3 | 5
|  | # of strucutred ministries established in the church plants (Limited to the church plants including Children incl ROPES, youth, young adults and the fellowship/care ministries) | 28 | 35
Children, Youth, and Young Adults are actively and variously engaged in influencing the world around them by living out and sharing their Christian testimony; At least 50% of Children, youth and young adults | 4.1 Children actively living out and sharing their Christian testimony | % of children living out and sharing their Christian testimony (home, school, play arenas etc) | 49% | 60%
| 4.2 Youth actively living out and sharing their Christian testimony | % of youth (ages13-17) involved actively living out and sharing their Christian testimony (understand, communicate and living out the gospel) | 13% | 45%
| 4.3 Young adults actively living out and sharing their Christian testimony | % of young adults (ages 18-29) actively living out their Christian testimony (understand, communicate and living out the gospel) | 16% | 45%
Governance and management structures are aligned and strengthened effectively overseeing the affairs of NBC and its growth; Alignment and strength of governance and management structures rated as good | 5.1 Governance and management structures are fully aligned to the changing structure of the church | % level of alignment across the entire NBC | 72% | 95%
| 5.2 Governance and management structures strengthened to effecitvely give oversight to the growing and dynamic church | Level of strengthening attained | 70% | 95%
| 5.3 Increased Registered Membership | % increased propotion of members | 31% | At least 50% of congregation at any one time are members
CRITICAL SUPPORT/ADMINISTRATIVE ITEMS |  |  |  |  | KIBRA: Staff Renumeration | [10 empty] | 4302322 | 0 | 4302322
[5 empty] | KIBRA: Staff and ministry team welfare | [10 empty] | 233000 | 0 | 233000
[5 empty] | KIBRA:Minor Repairs and maintanance | [10 empty] | 160000 | 0 | 160000
[5 empty] | KIBRA: Administrative costs | [10 empty] | 895000 | 0 | 895000
[5 empty] | SW: Transport and other admin costs | [10 empty] | 116000 |  | 116000
[5 empty] | KWALE: Staff Renumeration | [10 empty] | 1943121 |  | 1943121
[5 empty] | KWALE: LOWCUM( nurse reliever), probono services, | [10 empty] | 150000 |  | 150000
[5 empty] | KWALE:Repairs, renovations and developments: Develop the play ground in Kwale: Swings, slides so as to attract more children at the mission base and engage them in christan living.Holiday bible clubs. Develop youth friendly services and environment. | [10 empty] | 150000 |  | 150000
[5 empty] | KWALE:Transport, communication,WIFI & other administrative costs. | [10 empty] | 200000 | 0 | 200000
[5 empty] | Zonal pastoral care | [10 empty] | 100000 |  | 100000
[16 empty] | 22847733 | 2609562 | 20238171
| Signed by employee: |  |  | Date:
| Signed by Supervisor: |  |  | Date: