## Sheet1
Bishu House Project 2022
Trips/Quantity
Water &Transport | 10 | 300 | 3000
bricks | 1 | 9500 | 9500
Cement | 7 | 650 | 4550
Fundi Labor (2 days) | 2 | 2500 | 5000
Casuals (2 days) | 2 | 1250 | 2500
Mattress | 1 | 1900 | 1900
Bed | 1 | 3700 | 3700
Transport to carry bed | 1 | 300 | 300
Boda for water tank | 2 | 200 | 400
Mikashorina | 2 | 100 | 200
Transport for Iron sheets | 1 | 200 | 200
Mpesa charges | 1 | 201 | 201
0
0
0
0
Toal |  |  | 31451
Explanations
Water & Transport: The boda carried 6 jericans per trip for water. In all 60 jericans were used.
Casuals: The initial plan was one day for the work. However, the work spilled into two days that we had not planned.
Ironsheets: We took two iron sheets from Dima to put at the Verandah. But since it required a third day of work, there was no money to do so. The grandchild of the mzee volunteered to do the work for free. Unfortunately, he was not serious. So he keeps on saying he will do it.
Mpesa Charges: Obviously not a one transaction. Sent the Contractor for the bricks and cement Kshs. 14200 for both bricks and cement. Also bought bed via Mpesa.